## curated_for_you_by_you_2025-11-
Key | Issue Type | Parent | Summary | Status | Assignee | Sprint | Start date | Inferred start date | Due date | Inferred due date
CFYBY-1 | Epic |  | Web Application | To Do |  |  | 2025-09-21 | 2025-09-21 | 2025-10-21 | 2025-10-21
CFYBY-6 | Task | CFYBY-1 | Location Search / Search - Web page | Done | Jalen Gill | Minimum Viable Product |  | 2025-09-21 |  | 2025-10-21
CFYBY-7 | Task | CFYBY-1 | Genre / Search Web page | Done | Christos Markakis | Minimum Viable Product |  | 2025-09-21 |  | 2025-10-21
CFYBY-5 | Task | CFYBY-1 | User Landing Page | Done | Maya Rivera | Minimum Viable Product |  | 2025-09-21 |  | 2025-10-21
CFYBY-20 | Task | CFYBY-1 | Artist List Page | Done | Maya Rivera | Refining Frontend / Middleware |  | 2025-10-19 |  | 2025-11-16
CFYBY-25 | Task | CFYBY-1 | Comprehensive Middleware Testing | Done | Emmet Allen | Refining Frontend / Middleware |  | 2025-10-19 |  | 2025-11-16
CFYBY-9 | Task | CFYBY-1 | Artist Information Page | To Do
CFYBY-23 | Task | CFYBY-1 | Improve Accessibility and Responsiveness to Frontend | To Do
CFYBY-2 | Epic |  | API Data Integration | To Do |  |  | 2025-10-16 | 2025-10-16 | 2025-11-12 | 2025-11-12
CFYBY-19 | Task | CFYBY-2 | 3rd Party API Discovery | Done | Pete Adams | Minimum Viable Product |  | 2025-09-21 |  | 2025-10-21
CFYBY-8 | Task | CFYBY-2 | 3rd Party API Ingestion | Done | Pete Adams | Minimum Viable Product |  | 2025-09-21 |  | 2025-10-21
CFYBY-11 | Task | CFYBY-2 | Introduce Artist Discography Data | Done | Christos Markakis | Refining Frontend / Middleware |  | 2025-10-19 |  | 2025-11-16
CFYBY-10 | Task | CFYBY-2 | Configure Data Storage | Done | Pete Adams | Refining Frontend / Middleware |  | 2025-10-19 |  | 2025-11-16
CFYBY-3 | Epic |  | Location Based Artist Data | To Do |  |  | 2025-11-07 | 2025-11-07 | 2025-12-04 | 2025-12-04
CFYBY-12 | Task | CFYBY-3 | Location Search | To Do
CFYBY-13 | Task | CFYBY-3 | Location Based Artist Search Data Retrieval | To Do
CFYBY-4 | Epic |  | Playlist/Music Recommendation | To Do |  |  | 2025-11-12 | 2025-11-12 | 2025-12-06 | 2025-12-06
CFYBY-16 | Task | CFYBY-4 | Display Artist Discography | Done | Jalen Gill | Refining Frontend / Middleware |  | 2025-10-19 |  | 2025-11-16
CFYBY-14 | Task | CFYBY-4 | Spotify OAuth Integration | To Do
CFYBY-15 | Task | CFYBY-4 | Spotify API Integration | To Do
CFYBY-17 | Task | CFYBY-4 | Playlist Creation | To Do
CFYBY-18 | Task | CFYBY-4 | Playlist Integration | To Do
CFYBY-26 | Epic |  | Application Hosting | To Do |  |  | 2025-11-17 | 2025-11-17 | 2025-12-03 | 2025-12-03
CFYBY-24 | Task | CFYBY-26 | Create Containerization Files for Cloud Hosting | Done | Emmet Allen | Refining Frontend / Middleware |  | 2025-10-19 |  | 2025-11-16
CFYBY-22 | Task | CFYBY-26 | Configure MiddleWare Hosting | To Do
CFYBY-21 | Task | CFYBY-26 | Configure FrontEnd Hosting | To Do