## Sheet1
ID | Epic | User Story | Goals | Acceptance Criteria | Test Cases | Points | Sprint
Artist List Page | Web Application | As a user, When I submit my search inputs, I want to be shown a webpage that has the results for that search. | Should have artist information cards presented on the page. Should integrate with the Middleware API to retrieve the search results. | Acceptance Criteria User can See artists info on the webpage. Artist info card must include: Name City Country Should integrate with the Middleware API to retrieve the search results. | Happy Path: Successful search displays multiple artists with complete information Given I am on the search results page And the Middleware API is available and returns a list of artists When the search inputs are successfully submitted Then I should see the search results webpage And the webpage should display multiple artist information cards And for each artist, I should see their Name, City, and Country Sad Path: Search returns no results Given I am on the search results page And the Middleware API is available but returns an empty list of artists When the search inputs are successfully submitted Then I should see the search results webpage And I should see a clear message indicating "No artists found for your search" And I should not see any artist information cards Neutral Path: Artist data is partially complete Given I am on the search results page And the Middleware API returns an artist where the "City" or "Country" field is null When the search inputs are successfully submitted Then I should see the artist's Name displayed on an information card And for the missing fields, I should see a clear indicator like "N/A" | 3 | 2
Display Artist Discography | API Data Integration | As a user, When I am on the artist information page, I want to be able to see the artist discography if available. | Should have a list of albums / songs made by the artist Should display the artist information in a subsection of the page List should contain no more than 5 songs | User can see A small list of songs Songs need to pertain to the artist An Artist's core information (name, etc.) is visible alongside the discography | Happy Path: Artist has 5 or more songs/albums and displays the maximum allowed Given I am on the artist information page And the API provides 10 songs/albums for the artist When the page loads the discography section Then I should see the artist's core information displayed And I should see a list of songs/albums And the list should contain exactly 5 songs/albums Sad Path: Artist has no discography data available Given I am on the artist information page And the API provides an empty list for the artist's discography When the page loads the discography section Then I should see the artist's core information displayed And I should see a message indicating "No discography available" or similar And I should not see any song or album items listed | 3 | 2
Introduce Artist Discography Data | API Data Integration | As a middleware, When I make a call to the CFYBY database I want to be able to pull artist info objects that include artist discography data. | Data should be in the artist object Data is artist specific If no discography data, data should be an empty JSON object | Acceptance Criteria Middleware Should be able to query discography Should recieve artist discography with artist data | Happy Path: Middleware successfully pulls an artist with a full discography Given the CFYBY database is available And the requested artist has existing discography data When the Middleware makes a single query for the artist object Then the Middleware should receive a response with a 200 (OK) status And the response body should contain the main artist object And the artist object should contain a field named "albums" And the "albums" field should be a list of song/album objects Sad Path: Middleware handles a database error during retrieval Given the CFYBY database is unavailable or the query is malformed When the Middleware attempts to query the artist object Then the Middleware should log a database connection or query error And the Middleware should return an appropriate error status (e.g., 500 Internal Server Error) to the calling client | 5 | 2
Configure Data Storage | API Data Integration | As a middleware, When I receive a request, I want to be able to access the data that is stored in a cloud service. | Should be easily accessible Data should hold its integrity and structure Data should be hosted in a cloud service | Must be reachable by API key or token Data must have same JSON structure Data should be hosted on an accessible cloud service | Happy Path: Middleware successfully retrieves and validates cloud data structure Given the cloud data service is reachable via its endpoint And the Middleware has a valid authentication token/key When the Middleware makes a request to the cloud service Then the response status code should be 200 (OK) And the retrieved data should adhere to the predefined JSON schema And the retrieved data should contain the expected primary fields Sad Path: Middleware fails to access data with invalid credentials Given the cloud data service is reachable via its endpoint And the Middleware attempts to access the service with an invalid or expired token/key When the Middleware makes a request to the cloud service Then the response status code should be 401 (Unauthorized) or 403 (Forbidden) And the Middleware should log the access failure securely And the Middleware should return an appropriate error message to the calling client | 3 | 2
Create Containerization Files for Cloud Hosting | Application Hosting | As a developer When I want to run the full application I want to be able to do so by running the application and its components in docker | The application is able to be hosted within docker The README is updated to support initialization with both docker and on local | Developers can Run the application by following the ReadMe for starting up the docker containers Interact with the application without any regressions | Happy Path: Developer successfully starts the entire application stack using Docker Compose Given the developer has Docker installed on their machine And the developer has pulled the latest repository code When the developer executes the documented "docker-compose up" command Then all required application services (e.g., middleware, database) should start successfully And the developer should see logs indicating all services are "healthy" or "running" And the application should be reachable via the documented local host port | 1 | 2
Comprehensive Middleware Testing | Web Application | As a developer When I run the test for the middleware application I want to be shown all test cases for the middleware including happy and sad paths. | All endpoints of the middleware should be assigned a proper api test All test should validate data functionality and test case (happy/sad path) scenarios | Developers can Run pyunit test for middleware, where all test are green (pass) Can quickly understand the happy/sad paths for each test case | Happy Path: Middleware Test Suite successfully runs Happy Path tests Given the test environment is correctly configured (API keys valid, external services available) And the test runner executes all tests for the "/search" endpoint When the test case named "test_search_returns_multiple_artists_200" is run Then the test should assert that the response status code is 200 (OK) And the test should assert the response body contains a valid JSON list of artists And the test result should be "PASS" (green) Sad Path: Middleware Test Suite validates Sad Path for Invalid Request Given the test runner executes all tests for the "/artist/{id}" endpoint When the test case named "test_get_artist_invalid_id_returns_400" is run with a non-integer or malformed ID Then the test should assert that the response status code is 400 (Bad Request) And the test should assert that the error message clearly states the input validation failure And the test result should be "PASS" (green) | 2 | 2